## Gantt
Phase | Start | End | Milestone | Owner | Status
Initiation | 2025-01-01 | 2025-01-07 | Charter Approved | PM | Complete
Planning | 2025-01-08 | 2025-01-20 | Baseline Approved | PMO | Complete
Execution | 2025-01-21 | 2025-03-15 | Build Complete | IT Lead | In Progress
Testing | 2025-03-01 | 2025-03-20 | UAT Signoff | Business | Planned
Closure | 2025-03-21 | 2025-03-30 | Project Closed | PM | Planned