## Project Plan
Task | Start | End | Owner
Planning | 2026-03-12 | 2026-03-19 | PM
Requirements | 2026-03-19 | 2026-04-11 | Business Analyst
Design | 2026-04-11 | 2026-05-11 | Architect
Development | 2026-05-11 | 2026-07-10 | Engineering
Testing | 2026-07-10 | 2026-08-09 | QA
Deployment | 2026-08-09 | 2026-09-08 | DevOps

## Stakeholder Register
Stakeholder | Role | Influence | Communication
CEO | Executive | High | Monthly executive briefing
Project Sponsor | Sponsor | High | Weekly sponsor meeting
IT Director | Technical Lead | Medium | Bi‑weekly technical review
Operations Manager | Operations | Medium | Status updates
End Users | Users | Low | Training sessions

## Power Interest Matrix
Stakeholder | Power | Interest | Strategy
CEO | High | High | Manage Closely
Project Sponsor | High | High | Manage Closely
IT Director | Medium | Medium | Keep Satisfied
Operations Manager | Medium | High | Keep Informed
End Users | Low | Medium | Monitor

## Risk Register
Risk | Probability | Impact | Mitigation | Status
Budget overrun | Medium | High | Budget monitoring | Open
Integration complexity | Medium | High | Early integration testing | Open
Stakeholder resistance | Low | Medium | Stakeholder workshops | Monitoring

## RAID Log
Category | Description | Owner | Status
Risk | Budget overrun risk | PM | Open
Assumption | Stakeholders available for review meetings | Sponsor | Confirmed
Issue | Data integration delay | Engineering | Monitoring
Dependency | Third‑party API availability | Vendor | Pending

## Budget Tracker
Category | Budget | Actual | Variance
Software | 50000 | 45000 | 5000
Infrastructure | 30000 | 28000 | 2000
Labor | 120000 | 110000 | 10000
Training | 15000 | 12000 | 3000