## Dashboard
CORPORATE OPERATIONS CENTER ¦ PROJECT CONTROLS DASHBOARD
Status Date | 2026-09-11 | Project Start | 2026-01-12 | Contract Finish | 2027-03-19 | Approved Budget | 20600000 | Project Manager | Portfolio Simulation
Revised Budget |  | Forecast at Completion |  | Forecast Variance |  | Actual Cost to Date |  | Open RFIs |  | Open Risks
21057000 |  | 20550000 |  | 507000 |  | 10215000 |  | 3 |  | 8
Planned Progress |  | Actual Progress |  | Schedule Variance |  | Approved Changes |  | Open Actions |  | Recordable Incidents
51.68% |  | 49.85% |  | -1.824% |  | 564500 |  | 8 |  | 0
MANAGEMENT HEALTH SUMMARY | [6 empty] | NEXT 30 DAYS - KEY MILESTONES
Area | Health | Key Driver |  | Immediate Management Action |  |  | Milestone | Baseline | Forecast | Owner | Risk
Schedule | AMBER | Weather-tight milestone and MEP Area A are behind plan |  | Recover south elevation framing; protect dry-in milestone |  |  | AHU / RTU crane set | 09/18/2026 | 09/17/2026 | Mechanical | Low
Cost | AMBER | Forecast remains within budget but contingency is tightening |  | Escalate elective owner changes; protect remaining contingency |  |  | Weather-tight milestone | 09/25/2026 | 09/29/2026 | GC / Envelope | High
Procurement | GREEN | Major long-leads released; electrical gear remains on critical watch |  | Hold weekly factory call and maintain expedite decision gate |  |  | Electrical gear ship | 09/28/2026 | 09/28/2026 | Electrical | Medium
Safety | GREEN | Zero recordables; one open scaffold observation |  | Close observation before next shift; continue leading-edge audits |  |  | Interior framing start | 09/28/2026 | 09/30/2026 | GC / Framing | Medium
Quality | AMBER | One open MEP rough-in deficiency at Grid C7 |  | Close clash and reinspect before downstream enclosure |  |  | Area A MEP rough-in complete | 10/02/2026 | 10/09/2026 | MEP | High

## Master_Schedule
WBS | Phase | Activity | Owner | Planned Start | Planned Finish | Actual Start | Actual Finish | Duration (d) | Predecessor | Planned % | Actual % | Status | Variance (pp) | Critical? | Notes
1.1 | Preconstruction | Owner program validation | PM | 2026-01-12 | 2026-01-23 | 2026-01-12 | 2026-01-22 | 12 |  | 100% | 100% | Complete | 0% | No | Program signed off one day early
1.2 | Preconstruction | Design development / 60% CDs | Architect | 2026-01-19 | 2026-02-20 | 2026-01-19 | 2026-02-24 | 33 | 1.1 | 100% | 100% | Complete | 0% | Yes | Four-day delay absorbed by bid prep
1.3 | Preconstruction | 100% construction documents | Architect | 2026-02-23 | 2026-03-27 | 2026-02-25 | 2026-04-02 | 33 | 1.2 | 100% | 100% | Complete | 0% | Yes | MEP coordination drove six-day slip
1.4 | Preconstruction | Permit review and issuance | PM/Architect | 2026-03-02 | 2026-04-10 | 2026-03-02 | 2026-04-14 | 40 | 1.3 | 100% | 100% | Complete | 0% | Yes | Permit issued 4/14
1.5 | Procurement | Bid packages and subcontract awards | PM | 2026-02-16 | 2026-04-03 | 2026-02-16 | 2026-04-07 | 47 | 1.2 | 100% | 100% | Complete | 0% | No | Major trades bought out
2.1 | Mobilization | Site mobilization / temporary controls | Superintendent | 2026-04-13 | 2026-04-24 | 2026-04-15 | 2026-04-24 | 12 | 1.4,1.5 | 100% | 100% | Complete | 0% | Yes | Mobilization started after permit
2.2 | Sitework | Clearing and erosion controls | Sitework Sub | 2026-04-20 | 2026-05-08 | 2026-04-22 | 2026-05-11 | 19 | 2.1 | 100% | 100% | Complete | 0% | Yes | Rain impacted 3 days
2.3 | Sitework | Mass grading and underground utilities | Sitework Sub | 2026-05-04 | 2026-06-12 | 2026-05-06 | 2026-06-18 | 40 | 2.2 | 100% | 100% | Complete | 0% | Yes | Utility conflict required RFI-006
3.1 | Foundations | Footings and grade beams | Concrete Sub | 2026-05-25 | 2026-06-19 | 2026-05-28 | 2026-06-24 | 26 | 2.3 | 100% | 100% | Complete | 0% | Yes | Recovered two days with added crew
3.2 | Foundations | Slab-on-grade | Concrete Sub | 2026-06-15 | 2026-07-10 | 2026-06-20 | 2026-07-15 | 26 | 3.1 | 100% | 100% | Complete | 0% | Yes | Passed FF/FL testing
4.1 | Structure | Structural steel fabrication | Steel Sub | 2026-04-20 | 2026-07-03 | 2026-04-22 | 2026-07-10 | 75 | 1.5 | 100% | 100% | Complete | 0% | Yes | Long-lead shop drawing cycle
4.2 | Structure | Structural steel erection | Steel Sub | 2026-07-13 | 2026-08-21 | 2026-07-16 | 2026-08-28 | 40 | 3.2,4.1 | 100% | 100% | Complete | 0% | Yes | Completed one week late
4.3 | Structure | Metal deck and concrete elevated slab | Steel/Concrete | 2026-08-03 | 2026-09-04 | 2026-08-10 |  | 33 | 4.2 | 100% | 88% | In Progress | -12% | Yes | Deck pour sequence recovering schedule
5.1 | Envelope | Exterior framing and sheathing | Framing Sub | 2026-08-17 | 2026-09-25 | 2026-08-24 |  | 40 | 4.2 | 75% | 62% | In Progress | -13% | Yes | South elevation 5 days behind
5.2 | Envelope | Roofing system | Roofing Sub | 2026-08-31 | 2026-09-25 | 2026-09-03 |  | 26 | 4.3 | 45% | 38% | In Progress | -7% | Yes | Weather-tight target 9/29
5.3 | Envelope | Curtain wall / storefront | Glazing Sub | 2026-09-07 | 2026-10-16 | 2026-09-09 |  | 40 | 5.1 | 15% | 8% | In Progress | -7% | No | Frames arriving in 2 lots
6.1 | MEP | Underground electrical and plumbing | MEP Subs | 2026-05-18 | 2026-07-17 | 2026-05-20 | 2026-07-21 | 61 | 2.3 | 100% | 100% | Complete | 0% | No | Completed
6.2 | MEP | MEP overhead rough-in - Area A | MEP Subs | 2026-08-24 | 2026-10-02 | 2026-08-31 |  | 40 | 4.3 | 50% | 35% | In Progress | -15% | Yes | Coordination issue at grid C7
6.3 | MEP | MEP overhead rough-in - Area B | MEP Subs | 2026-09-14 | 2026-10-23 |  |  | 40 | 6.2 | 0% | 0% | Not Started | 0% | Yes | Release after Area A inspection
6.4 | MEP | Main electrical gear delivery | Electrical Sub | 2026-05-04 | 2026-10-09 | 2026-05-04 |  | 159 | 1.5 | 80% | 76% | In Progress | -4% | Yes | Factory ship date confirmed 9/28
6.5 | MEP | AHU / RTU delivery and set | Mechanical Sub | 2026-05-11 | 2026-09-18 | 2026-05-11 |  | 131 | 1.5 | 92% | 88% | In Progress | -4% | Yes | Crane set planned 9/17
7.1 | Interiors | Interior metal framing | Framing Sub | 2026-09-28 | 2026-11-06 |  |  | 40 | 5.2,6.2 | 0% | 0% | Not Started | 0% | Yes | Start after dry-in
7.2 | Interiors | Drywall / tape / finish | Drywall Sub | 2026-10-19 | 2026-12-04 |  |  | 47 | 7.1 | 0% | 0% | Not Started | 0% | Yes
7.3 | Interiors | Ceilings and flooring | Finishes Subs | 2026-11-23 | 2027-01-15 |  |  | 54 | 7.2 | 0% | 0% | Not Started | 0% | No
7.4 | Interiors | Millwork / doors / hardware | Carpentry Sub | 2026-11-30 | 2027-01-22 |  |  | 54 | 7.2 | 0% | 0% | Not Started | 0% | No
7.5 | Interiors | Painting and final finishes | Painting Sub | 2026-12-07 | 2027-01-29 |  |  | 54 | 7.2 | 0% | 0% | Not Started | 0% | No
8.1 | Sitework | Paving, curb, sidewalks | Sitework Sub | 2026-10-05 | 2026-11-13 |  |  | 40 | 5.1 | 0% | 0% | Not Started | 0% | No
8.2 | Sitework | Landscaping and site furnishings | Landscape Sub | 2027-01-04 | 2027-02-05 |  |  | 33 | 8.1 | 0% | 0% | Not Started | 0% | No
9.1 | Commissioning | MEP startup and controls checkout | CxA/MEP | 2027-01-11 | 2027-02-12 |  |  | 33 | 6.4,6.5,7.3 | 0% | 0% | Not Started | 0% | Yes
9.2 | Commissioning | TAB / functional performance testing | CxA | 2027-02-01 | 2027-02-26 |  |  | 26 | 9.1 | 0% | 0% | Not Started | 0% | Yes
9.3 | Closeout | Punch list and deficiency correction | PM/Superintendent | 2027-02-15 | 2027-03-05 |  |  | 19 | 7.5,9.2 | 0% | 0% | Not Started | 0% | Yes
9.4 | Closeout | Owner training / O&M turnover | PM/CxA | 2027-02-22 | 2027-03-12 |  |  | 19 | 9.1 | 0% | 0% | Not Started | 0% | No
9.5 | Closeout | Certificate of Occupancy | PM/Architect | 2027-03-08 | 2027-03-12 |  |  | 5 | 9.3 | 0% | 0% | Not Started | 0% | Yes
9.6 | Closeout | Final completion / handover | PM | 2027-03-15 | 2027-03-19 |  |  | 5 | 9.4,9.5 | 0% | 0% | Not Started | 0% | Yes

## Budget_Cost
Cost Code | Cost Category | Original Budget | Approved Changes | Revised Budget | Committed | Actual Cost to Date | ETC | Forecast at Completion | Variance to Budget | % Committed | % Spent | Status | Notes
01-100 | General Conditions | 1350000 | 125000 | 1475000 | 1445000 | 970000 | 510000 | 1480000 | -5000 | 97.97% | 65.76% | Watch | Extended supervision due to early schedule slippage
02-200 | Sitework & Utilities | 1820000 | 85000 | 1905000 | 1880000 | 1735000 | 170000 | 1905000 | 0 | 98.69% | 91.08% | On Budget | Utility conflict resolved
03-300 | Concrete | 2050000 | 45000 | 2095000 | 2075000 | 1960000 | 155000 | 2115000 | -20000 | 99.05% | 93.56% | On Budget | Minor premium for recovery crew
05-500 | Structural Steel | 2790000 | 210000 | 3000000 | 2945000 | 2385000 | 590000 | 2975000 | 25000 | 98.17% | 79.5% | Watch | Escalation and connection redesign
07-700 | Roofing & Waterproofing | 840000 | 0 | 840000 | 810000 | 180000 | 640000 | 820000 | 20000 | 96.43% | 21.43% | On Budget | Buyout savings retained
08-800 | Glazing / Doors / Hardware | 1260000 | 95000 | 1355000 | 1325000 | 230000 | 1090000 | 1320000 | 35000 | 97.79% | 16.97% | Watch | Storefront upgrade approved
09-900 | Interiors / Finishes | 2190000 | -65000 | 2125000 | 2080000 | 250000 | 1810000 | 2060000 | 65000 | 97.88% | 11.76% | On Budget | VE package reduced ceiling scope
21-2300 | Fire Protection | 510000 | 0 | 510000 | 495000 | 145000 | 345000 | 490000 | 20000 | 97.06% | 28.43% | On Budget
22-2200 | Plumbing | 780000 | 42000 | 822000 | 805000 | 315000 | 500000 | 815000 | 7000 | 97.93% | 38.32% | On Budget | Added floor sinks
23-2300 | HVAC / Controls | 1810000 | 120000 | 1930000 | 1885000 | 525000 | 1410000 | 1935000 | -5000 | 97.67% | 27.2% | Watch | Controls integration allowance
26-2600 | Electrical / Low Voltage | 2030000 | 165000 | 2195000 | 2135000 | 635000 | 1545000 | 2180000 | 15000 | 97.27% | 28.93% | Watch | Main gear expedite allowance
31-3200 | Paving / Landscaping | 760000 | 0 | 760000 | 720000 | 85000 | 615000 | 700000 | 60000 | 94.74% | 11.18% | On Budget
00-900 | Design / Permits / Testing | 790000 | 55000 | 845000 | 835000 | 690000 | 145000 | 835000 | 10000 | 98.82% | 81.66% | On Budget | Additional special inspections
00-950 | Owner FF&E / IT Allowance | 900000 | 0 | 900000 | 610000 | 110000 | 510000 | 620000 | 280000 | 67.78% | 12.22% | On Budget | Owner-direct packages
00-990 | Construction Contingency | 720000 | -420000 | 300000 | 0 | 0 | 300000 | 300000 | 0 | 0% | 0% | Watch | $420K allocated through approved changes

## Procurement
Package | Trade/Vendor | Scope | Budget | Bid Due | Award Date | Submittal Due | Required On Site | Current Forecast | Lead Time (wks) | Status | Owner | Risk/Action
BP-01 | Carolina Earthworks | Sitework / utilities | 1820000 | 2026-02-27 | 2026-03-13 | 2026-03-27 | 2026-04-20 | 2026-04-22 | 5 | Complete | PM | Closed
BP-02 | Piedmont Concrete | Foundations / slabs | 2050000 | 2026-03-06 | 2026-03-20 | 2026-04-03 | 2026-05-25 | 2026-05-28 | 8 | Complete | PM | Closed
BP-03 | SteelWorks Southeast | Structural steel | 2790000 | 2026-02-20 | 2026-03-06 | 2026-03-20 | 2026-07-13 | 2026-07-16 | 18 | Complete | PM | Late detailing; recovery complete
BP-04 | Atlantic Roofing | Roofing | 840000 | 2026-03-13 | 2026-03-27 | 2026-04-10 | 2026-08-31 | 2026-09-03 | 12 | In Progress | PM | Monitor membrane delivery
BP-05 | ClearView Glazing | Curtain wall / storefront | 1260000 | 2026-03-13 | 2026-03-27 | 2026-04-10 | 2026-09-07 | 2026-09-09 | 20 | In Progress | PM | Frames split into two shipments
BP-06 | Precision Mechanical | HVAC / controls | 1810000 | 2026-02-27 | 2026-03-13 | 2026-03-27 | 2026-09-14 | 2026-09-17 | 24 | In Progress | PM | RTU crane set locked for 9/17
BP-07 | Triad Electrical | Electrical / low voltage | 2030000 | 2026-02-27 | 2026-03-13 | 2026-03-27 | 2026-10-09 | 2026-10-05 | 28 | In Progress | PM | Gear ship 9/28; 4-day float
BP-08 | Interior Systems Inc. | Framing / drywall / ceilings | 2190000 | 2026-04-03 | 2026-04-17 | 2026-05-01 | 2026-09-28 | 2026-09-28 | 10 | Awarded | PM | Release Area A material now
BP-09 | FinishWorks | Flooring / paint | 940000 | 2026-05-01 | 2026-05-15 | 2026-06-01 | 2026-11-23 | 2026-11-23 | 12 | Awarded | PM | Mockups due 10/16
BP-10 | OfficeTech Integrators | AV / access control / data | 610000 | 2026-06-12 | 2026-06-26 | 2026-07-10 | 2027-01-04 | 2027-01-04 | 18 | Awarded | Owner IT | Coordinate with ceilings

## RFI_Log
RFI # | Date Submitted | Discipline | Subject | Submitted By | Ball In Court | Due Date | Answered Date | Status | Schedule Impact (days) | Cost Impact | Related CO | Resolution / Decision
RFI-001 | 2026-04-27 | Civil | Storm line invert conflict at east drive | Sitework Sub | Civil Engineer | 2026-05-01 | 2026-04-30 | Closed | 0 | 0 |  | Revise invert and add cleanout
RFI-002 | 2026-05-18 | Structural | Footing F12 clashes with telecom ductbank | Concrete Sub | Structural Engineer | 2026-05-22 | 2026-05-21 | Closed | 0 | 12500 | CO-002 | Shift footing 18 inches west
RFI-003 | 2026-06-02 | Architectural | Lobby stone backing detail | Framing Sub | Architect | 2026-06-08 | 2026-06-09 | Closed | 1 | 4500 |  | Supplemental stud framing approved
RFI-004 | 2026-06-19 | Structural | Beam camber tolerance at grid D | Steel Sub | Structural Engineer | 2026-06-25 | 2026-06-24 | Closed | 0 | 0 |  | Accept per tolerance; field survey required
RFI-005 | 2026-07-07 | Mechanical | Roof curb opening dimensions | Mechanical Sub | Architect/MEP | 2026-07-13 | 2026-07-10 | Closed | 0 | 0 |  | Use vendor-certified curb dimensions
RFI-006 | 2026-05-29 | Civil | Unknown utility crossing north service yard | Sitework Sub | Civil Engineer | 2026-06-04 | 2026-06-08 | Closed | 3 | 68500 | CO-004 | Reroute sanitary around existing fiber bank
RFI-007 | 2026-07-27 | Architectural | Storefront head condition at canopy | Glazing Sub | Architect | 2026-08-03 | 2026-08-05 | Closed | 2 | 18000 | CO-006 | Add steel tube support at head
RFI-008 | 2026-08-11 | MEP | Duct / sprinkler clash above training room | Mechanical Sub | MEP Engineer | 2026-08-17 | 2026-08-14 | Closed | 0 | 0 |  | Raise branch line 4 inches
RFI-009 | 2026-08-20 | Electrical | Generator feeder routing through shear wall | Electrical Sub | MEP/Structural | 2026-08-26 | 2026-08-31 | Closed | 2 | 22500 | CO-008 | Core sleeve detail issued
RFI-010 | 2026-08-31 | Architectural | Exterior panel transition at loading dock | Envelope Sub | Architect | 2026-09-04 | 2026-09-08 | Answered | 1 | 7500 |  | Revised flashing detail A-521
RFI-011 | 2026-09-02 | Mechanical | AHU condensate routing at mezzanine | Mechanical Sub | MEP Engineer | 2026-09-09 | 2026-09-09 | Answered | 0 | 3200 |  | Route to nearby hub drain
RFI-012 | 2026-09-04 | Structural | Deck penetration reinforcing at RTU-3 | Steel Sub | Structural Engineer | 2026-09-10 | 2026-09-10 | Answered | 0 | 6400 |  | Add angle frame per SK-S14
RFI-013 | 2026-09-08 | Electrical | Lighting control zone revision in open office | Electrical Sub | Architect/Owner | 2026-09-14 |  | Open | 0 | 18000 | PCO-012 | Owner decision pending
RFI-014 | 2026-09-09 | Architectural | Door 214 hardware function | Door Sub | Architect | 2026-09-15 |  | Open | 0 | 0 |  | Confirm electrified panic hardware
RFI-015 | 2026-09-10 | MEP | Domestic water meter backflow arrangement | Plumbing Sub | MEP Engineer | 2026-09-16 |  | Open | 0 | 0 |  | Awaiting utility confirmation

## Submittal_Log
Submittal # | Spec Section | Package | Description | Trade | Submitted | Review Due | Returned | Status | Rev | Required On Site | Days Float | Notes
SUB-001 | 03 30 00 | BP-02 | Concrete mix designs | Piedmont Concrete | 2026-03-30 | 2026-04-06 | 2026-04-03 | Approved | 0 | 2026-05-25 | 52
SUB-002 | 05 12 00 | BP-03 | Structural steel shop drawings | SteelWorks Southeast | 2026-03-23 | 2026-04-06 | 2026-04-14 | Revise & Resubmit | 0 | 2026-06-01 | 48 | Second cycle expedited
SUB-003 | 05 12 00 | BP-03 | Structural steel shop drawings - Rev 1 | SteelWorks Southeast | 2026-04-17 | 2026-04-24 | 2026-04-23 | Approved | 1 | 2026-06-01 | 39 | Released to fabrication
SUB-004 | 07 54 23 | BP-04 | TPO roofing system | Atlantic Roofing | 2026-04-13 | 2026-04-27 | 2026-04-24 | Approved | 0 | 2026-08-31 | 129
SUB-005 | 08 41 13 | BP-05 | Aluminum storefront / curtain wall | ClearView Glazing | 2026-04-20 | 2026-05-04 | 2026-05-07 | Revise & Resubmit | 0 | 2026-09-07 | 123 | Head condition revised
SUB-006 | 08 41 13 | BP-05 | Storefront / curtain wall - Rev 1 | ClearView Glazing | 2026-05-11 | 2026-05-18 | 2026-05-18 | Approved | 1 | 2026-09-07 | 112 | Released
SUB-007 | 23 73 00 | BP-06 | Packaged rooftop units | Precision Mechanical | 2026-03-30 | 2026-04-13 | 2026-04-10 | Approved | 0 | 2026-09-14 | 157 | Long lead released
SUB-008 | 26 24 13 | BP-07 | Main switchboard / distribution gear | Triad Electrical | 2026-03-23 | 2026-04-06 | 2026-04-08 | Approved | 0 | 2026-10-09 | 184 | Critical long lead
SUB-009 | 09 29 00 | BP-08 | Gypsum board assemblies | Interior Systems Inc. | 2026-07-13 | 2026-07-27 | 2026-07-24 | Approved | 0 | 2026-09-28 | 66
SUB-010 | 09 51 00 | BP-08 | Acoustical ceiling systems | Interior Systems Inc. | 2026-08-03 | 2026-08-17 | 2026-08-18 | Approved | 0 | 2026-11-23 | 97
SUB-011 | 09 65 00 | BP-09 | Resilient flooring samples | FinishWorks | 2026-08-17 | 2026-08-31 | 2026-08-28 | Approved | 0 | 2026-11-23 | 87 | Mockup required
SUB-012 | 09 91 00 | BP-09 | Paint color samples | FinishWorks | 2026-08-24 | 2026-09-07 | 2026-09-04 | Approved | 0 | 2026-12-07 | 94
SUB-013 | 28 13 00 | BP-10 | Access control head-end | OfficeTech Integrators | 2026-08-31 | 2026-09-14 |  | Submitted | 0 | 2027-01-04 | 112 | Review due
SUB-014 | 27 41 16 | BP-10 | AV systems equipment rack | OfficeTech Integrators | 2026-09-08 | 2026-09-22 |  | Submitted | 0 | 2027-01-04 | 104

## Change_Log
Change # | Date | Title | Origin | Reason | ROM / Proposed | Approved Amount | Status | Budget Code | Schedule Impact (days) | Owner Decision Due | Notes
CO-001 | 2026-04-21 | Permit comment revisions | AHJ | Code / permit | 38000 | 38000 | Approved | 00-900 | 0 | 2026-04-24 | Added fire-rated shaft detail
CO-002 | 2026-05-21 | Footing relocation at telecom ductbank | RFI-002 | Unforeseen condition | 12500 | 12500 | Approved | 03-300 | 0 | 2026-05-26
CO-003 | 2026-06-10 | Owner conference room AV rough-in | Owner | Scope addition | 42000 | 42000 | Approved | 26-2600 | 0 | 2026-06-15
CO-004 | 2026-06-08 | Sanitary reroute at fiber bank | RFI-006 | Existing condition | 68500 | 68500 | Approved | 02-200 | 3 | 2026-06-10
CO-005 | 2026-07-02 | Structural steel connection redesign | Structural | Design coordination | 106000 | 106000 | Approved | 05-500 | 2 | 2026-07-07
CO-006 | 2026-08-05 | Canopy storefront steel support | RFI-007 | Design coordination | 18000 | 18000 | Approved | 08-800 | 2 | 2026-08-10
CO-007 | 2026-08-12 | Floor sink additions | Owner/Operations | Scope addition | 42000 | 42000 | Approved | 22-2200 | 0 | 2026-08-17
CO-008 | 2026-08-31 | Generator feeder wall sleeve | RFI-009 | Design coordination | 22500 | 22500 | Approved | 26-2600 | 2 | 2026-09-03
CO-009 | 2026-09-01 | Storefront performance upgrade | Owner | Scope enhancement | 95000 | 95000 | Approved | 08-800 | 0 | 2026-09-04
CO-010 | 2026-09-03 | HVAC controls integration allowance | MEP | Integration risk | 120000 | 120000 | Approved | 23-2300 | 0 | 2026-09-08
PCO-011 | 2026-09-08 | Expedite electrical gear freight | Electrical | Schedule recovery | 65000 | 0 | Pricing | 26-2600 | -4 | 2026-09-15 | Use only if factory ship slips beyond 9/30
PCO-012 | 2026-09-08 | Open office lighting control revision | Owner | Scope change | 18000 | 0 | Potential | 26-2600 | 0 | 2026-09-18 | Pending owner standards decision

## Risk_Register
Risk ID | Category | Risk Statement | Probability (1-5) | Impact (1-5) | Score | Level | Trigger | Mitigation / Response | Owner | Target Date | Status | Residual Score
R-01 | Schedule | Electrical gear delivery slips beyond required date | 3 | 5 | 15 | High | Factory ship slips past 9/30 | Weekly factory calls; preapprove air/expedite decision; temporary power contingency | PM | 2026-09-30 | Open | 8
R-02 | Schedule | Building not weather-tight before interior framing | 3 | 5 | 15 | High | Roof / curtain wall forecast exceeds 9/29 | Daily envelope huddles; split storefront shipments; temporary dry-in membrane | Superintendent | 2026-09-29 | Open | 9
R-03 | Cost | Remaining contingency is consumed by owner changes | 4 | 4 | 16 | High | Uncommitted contingency below $200K | Monthly change review; require owner funding for elective scope; freeze finishes by 10/1 | PM | 2026-10-01 | Open | 8
R-04 | Quality | Water intrusion at curtain wall transitions | 2 | 5 | 10 | Medium | Failed mockup / first water test | Full-size mockup; envelope consultant review; 100% transition inspection | QA/QC Lead | 2026-10-02 | Open | 4
R-05 | Safety | Falls during steel/deck/envelope overlap | 2 | 5 | 10 | Medium | Multiple trades working leading edges | 100% tie-off; controlled access zones; daily leading-edge audit | Safety Manager | 2026-09-25 | Open | 4
R-06 | Coordination | MEP clashes cause rework above ceilings | 3 | 4 | 12 | High | Unresolved clash tickets >10 | Weekly BIM clash meeting; sign-off by zone before rough-in | MEP Coordinator | 2026-09-18 | Open | 6
R-07 | Stakeholder | Owner late decisions delay finish procurement | 3 | 4 | 12 | High | Decision log overdue >5 business days | Decision due-date dashboard; escalation at OAC; default option identified | PM | 2026-09-25 | Open | 6
R-08 | Closeout | Incomplete O&M / training documents delay turnover | 2 | 4 | 8 | Medium | Subcontractor closeout >30 days late | Closeout requirements enforced with pay apps; monthly completeness audit | Project Engineer | 2027-01-15 | Open | 3

## Issues_Log
Issue ID | Date Opened | Issue | Impact | Owner | Priority | Due Date | Status | Decision / Next Step | Closed Date
I-001 | 2026-08-24 | Steel erection completion slipped one week | Downstream envelope / MEP access | Superintendent | High | 2026-09-02 | Complete | Added Saturday crew and resequenced deck pours | 2026-09-02
I-002 | 2026-09-01 | South elevation framing productivity below plan | Weather-tight milestone at risk | Superintendent | High | 2026-09-16 | In Progress | Add second lift and dedicated material runner
I-003 | 2026-09-04 | Open office lighting control standard unresolved | Potential owner change and rework | Owner PM | Medium | 2026-09-18 | Open | Owner to choose standard package
I-004 | 2026-09-09 | MEP clash at grid C7 training room | Rough-in delay in Area A | MEP Coordinator | High | 2026-09-14 | In Progress | Issue coordinated spool sketch
I-005 | 2026-09-10 | Storefront delivery split; second lot date unconfirmed | South elevation dry-in | PM | High | 2026-09-15 | Open | Vendor to confirm second-lot ship notice

## Safety_Log
Date | Event Type | Location | Description | Severity | Responsible Party | Immediate Action | Corrective Action | Status | Recordable?
2026-04-20 | Observation | Site perimeter | Missing cap on exposed rebar | Medium | Sitework Sub | Area barricaded | Install approved rebar caps and inspect all perimeter steel | Closed | No
2026-05-14 | Near Miss | Excavation | Spoil pile too close to trench edge | High | Sitework Sub | Work stopped | Relocate spoils >2 ft; retrain competent person | Closed | No
2026-06-18 | Observation | Slab pour | Extension cord crossing wet work path | Low | Concrete Sub | Cord rerouted | Use overhead cord management | Closed | No
2026-07-29 | Near Miss | Steel erection | Loose bolt dropped from upper level | High | Steel Sub | Drop zone enlarged | Tool tethering and toe-board audit | Closed | No
2026-08-12 | Observation | Roof deck | Worker not maintaining 100% tie-off | Critical | Steel Sub | Worker removed from exposure | Stand-down; documented retraining; foreman spot checks | Closed | No
2026-08-27 | Observation | Loading zone | Forklift pedestrian separation inadequate | Medium | GC | Cones added | Painted pedestrian route and spotter requirement | Closed | No
2026-09-08 | First Aid | North stair | Minor hand cut while handling sheet metal | Low | Mechanical Sub | First aid administered | Glove compliance toolbox talk | Closed | No
2026-09-10 | Observation | South elevation | Scaffold toe board missing | High | Framing Sub | Platform tagged out | Replace toe board before use; scaffold audit | In Progress | No

## Quality_Log
QC ID | Date | Area / Trade | Inspection / Test | Requirement | Result | Deficiency | Responsible Party | Due Date | Status | Verification
QC-001 | 2026-05-28 | Foundations | Rebar pre-pour | Per structural drawings | Pass |  | Concrete Sub | 2026-05-28 | Accepted | Special inspector sign-off
QC-002 | 2026-06-24 | Foundations | Concrete cylinder test - 7 day | Design 4,000 psi | Pass |  | Concrete Sub | 2026-07-15 | Accepted | Average 3,220 psi at 7 days
QC-003 | 2026-07-15 | Slab | FF/FL testing | FF35 / FL25 | Pass |  | Concrete Sub | 2026-07-17 | Accepted | FF41 / FL29
QC-004 | 2026-08-04 | Steel | Bolt tension inspection | AISC/RCSC | Pass |  | Steel Sub | 2026-08-04 | Accepted | Inspector report filed
QC-005 | 2026-08-25 | Envelope | Air barrier substrate inspection | Manufacturer requirements | Fail | Fastener spacing / open joints | Framing Sub | 2026-08-28 | Corrected | Reinspection passed 8/28
QC-006 | 2026-09-02 | Roof | TPO seam probe test | 100% seams | Pass |  | Roofing Sub | 2026-09-02 | Accepted
QC-007 | 2026-09-09 | MEP Area A | Above-ceiling rough-in walk | Approved coordination model | Fail | Duct/sprinkler conflict grid C7 | MEP Subs | 2026-09-14 | Open | Reinspect after RFI resolution
QC-008 | 2026-09-10 | South Elevation | Exterior framing plumb/tolerance | 1/8 in over 10 ft | Pass |  | Framing Sub | 2026-09-10 | Accepted

## Stakeholders
Stakeholder | Organization / Role | Influence | Interest | Communication Need | Cadence | Channel | Owner | Success Measure
Executive Sponsor | Owner / COO | High | High | Budget, schedule, major risk, decisions | Monthly | Executive report | PM | No surprises; decisions within 3 days
Owner Project Manager | Owner | High | High | Daily decisions, change control, coordination | Weekly + as needed | OAC / email | PM | Decision log current
Facilities Director | Owner Operations | Medium | High | Maintainability, equipment access, training | Biweekly | Field walk / meeting | PM | Operations sign-off
Architect | Design Team | High | High | RFIs, submittals, design intent | Weekly | OAC / Procore-style logs | PM | Average RFI turnaround <5 days
MEP Engineers | Design Team | High | Medium | Coordination, field clarifications | Weekly | BIM / RFI | MEP Coordinator | Clashes closed before install
General Contractor Team | Delivery Team | High | High | Schedule, safety, quality, costs | Daily | Huddle / dashboard | PM | Milestones achieved
Subcontractors | Trade Partners | Medium | High | Look-ahead, constraints, safety, quality | Weekly | Trade meeting | Superintendent | PPC >80%
AHJ / Inspectors | Regulatory | High | Medium | Inspection readiness, code compliance | As required | Inspection request | Project Engineer | Pass first inspection
Finance | Owner Finance | Medium | Medium | Forecast, cash flow, change exposure | Monthly | Cost report | PM | Forecast accuracy +/-2%
IT / Security | Owner IT | Medium | High | AV/data/access control decisions | Biweekly | Coordination meeting | PM | Systems ready before move-in

## Meeting_Actions
Action ID | Meeting | Date Opened | Action | Owner | Due Date | Priority | Status | Dependency | Completion Note
A-001 | OAC | 2026-09-03 | Confirm storefront second-shipment date | PM | 2026-09-15 | High | In Progress | BP-05 | Vendor escalation underway
A-002 | Trade Coordination | 2026-09-08 | Resolve grid C7 duct/sprinkler clash | MEP Coordinator | 2026-09-14 | High | In Progress | RFI-013 | Coordinated sketch due 9/14
A-003 | OAC | 2026-09-10 | Owner select lighting control standard | Owner PM | 2026-09-18 | High | Open | PCO-012 | Three options issued
A-004 | Safety | 2026-09-10 | Close scaffold toe-board observation | Framing Foreman | 2026-09-11 | High | In Progress | Safety 9/10 | Reinspection scheduled
A-005 | Procurement | 2026-09-09 | Confirm electrical gear factory ship notice | Electrical PM | 2026-09-18 | High | Open | R-01 | Weekly vendor update
A-006 | Quality | 2026-09-09 | Reinspect MEP rough-in at training room | QA/QC Lead | 2026-09-15 | Medium | Open | QC-007 | After clash correction
A-007 | OAC | 2026-09-03 | Freeze Level 1 finish selections | Facilities Director | 2026-09-17 | Medium | In Progress | R-07 | Final samples in owner review
A-008 | Schedule | 2026-09-11 | Add second lift at south elevation | Superintendent | 2026-09-14 | High | Open | I-002 | Recovery plan approved

## Closeout
Item ID | Category | Requirement | Responsible Party | Planned Due | Actual / Forecast | Status | % Complete | Retention Link | Notes
C-001 | Permits | Final building inspection / CO | PM/Architect | 2027-03-12 | 2027-03-12 | Not Started | 0% | Final payment | AHJ inspection matrix maintained
C-002 | Commissioning | Functional performance testing | CxA / MEP | 2027-02-26 | 2027-02-26 | Not Started | 0% | MEP retention
C-003 | O&M Manuals | Approved electronic O&M manuals | All Trades | 2027-02-12 | 2027-02-19 | Not Started | 0% | 10% trade retention | Monthly completeness audit starts Nov
C-004 | Training | Owner equipment training | MEP / Vendors | 2027-03-05 | 2027-03-05 | Not Started | 0% | MEP retention | Record sessions
C-005 | As-Builts | Redline and final record drawings | All Trades | 2027-02-19 | 2027-02-26 | Not Started | 0% | 5% trade retention | Weekly redline spot checks
C-006 | Warranties | Warranty certificates and start dates | All Trades | 2027-03-05 | 2027-03-05 | Not Started | 0% | Final payment
C-007 | Punch List | Architect/owner punch complete | GC / Subs | 2027-03-05 | 2027-03-05 | Not Started | 0% | Final payment | Digital punch by room
C-008 | Training | IT / security systems turnover | OfficeTech | 2027-03-05 | 2027-03-05 | Not Started | 0% | Vendor final
C-009 | Financial | Final change reconciliation | PM / Finance | 2027-03-12 | 2027-03-12 | Not Started | 0% | GC final | No open PCOs at substantial completion
C-010 | Lessons Learned | Project retrospective and KPI closeout | PM | 2027-03-19 | 2027-03-19 | Not Started | 0% | N/A

## Categories
Schedule Status | Cost Status | RFI Status | Submittal Status | Change Status | Risk Level | Action Status | Safety Severity | QC Status | Closeout Status | Priority
Not Started | On Budget | Open | Not Submitted | Potential | Low | Open | Low | Open | Not Started | Low
In Progress | Watch | Answered | Submitted | Pricing | Medium | In Progress | Medium | Corrected | In Progress | Medium
Complete | Over Budget | Closed | Approved | Approved | High | Complete | High | Accepted | Complete | High
Delayed |  | Void | Revise & Resubmit | Rejected | Critical |  | Critical | Rejected | Blocked | Critical

## CPM_Gantt
WBS | Activity | Pred. | Baseline Start | Baseline Finish | Forecast Start | Forecast Finish | Dur. | Critical | Float (d) | Variance (d) | Status | GANTT TIMELINE (weekly)
1.1 | Owner program validation |  | 2026-01-12 | 2026-01-23 | 2026-01-12 | 2026-01-22 | 12 | No | 7 | -1 | Complete | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-26 | 2026-06-02 | 2026-06-09 | 2026-06-16 | 2026-06-23 | 2026-06-30 | 2026-07-07 | 2026-07-14 | 2026-07-21 | 2026-07-28 | 2026-08-04 | 2026-08-11 | 2026-08-18 | 2026-08-25 | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24 | 2026-12-01 | 2026-12-08 | 2026-12-15 | 2026-12-22 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-19 | 2027-01-26 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-02-23 | 2027-03-02 | 2027-03-09 | 2027-03-16 | 2027-03-23 | 2027-03-30
1.2 | Design development / 60% CDs | 1.1 | 2026-01-19 | 2026-02-20 | 2026-01-19 | 2026-02-24 | 33 | Yes | 0 | 4 | Complete | ■ | ■
1.3 | 100% construction documents | 1.2 | 2026-02-23 | 2026-03-27 | 2026-02-25 | 2026-04-02 | 33 | Yes | 0 | 6 | Complete |  | ■ | ■ | ■ | ■ | ■ | ■
1.4 | Permit review and issuance | 1.3 | 2026-03-02 | 2026-04-10 | 2026-03-02 | 2026-04-14 | 40 | Yes | 0 | 4 | Complete | [7 empty] | ■ | ■ | ■ | ■ | ■
1.5 | Bid packages and subcontract awards | 1.2 | 2026-02-16 | 2026-04-03 | 2026-02-16 | 2026-04-07 | 47 | No | 7 | 4 | Complete | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■
2.1 | Site mobilization / temporary controls | 1.4,1.5 | 2026-04-13 | 2026-04-24 | 2026-04-15 | 2026-04-24 | 12 | Yes | 0 | 0 | Complete | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
2.2 | Clearing and erosion controls | 2.1 | 2026-04-20 | 2026-05-08 | 2026-04-22 | 2026-05-11 | 19 | Yes | 0 | 3 | Complete | [14 empty] | ■
2.3 | Mass grading and underground utilities | 2.2 | 2026-05-04 | 2026-06-12 | 2026-05-06 | 2026-06-18 | 40 | Yes | 0 | 6 | Complete | [15 empty] | ■ | ■
3.1 | Footings and grade beams | 2.3 | 2026-05-25 | 2026-06-19 | 2026-05-28 | 2026-06-24 | 26 | Yes | 0 | 5 | Complete | [17 empty] | ■ | ■ | ■ | ■ | ■ | ■
3.2 | Slab-on-grade | 3.1 | 2026-06-15 | 2026-07-10 | 2026-06-20 | 2026-07-15 | 26 | Yes | 0 | 5 | Complete | [20 empty] | ■ | ■ | ■ | ■
4.1 | Structural steel fabrication | 1.5 | 2026-04-20 | 2026-07-03 | 2026-04-22 | 2026-07-10 | 75 | Yes | 0 | 7 | Complete | [23 empty] | ■ | ■ | ■ | ■
4.2 | Structural steel erection | 3.2,4.1 | 2026-07-13 | 2026-08-21 | 2026-07-16 | 2026-08-28 | 40 | Yes | 0 | 7 | Complete | [15 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
4.3 | Metal deck and concrete elevated slab | 4.2 | 2026-08-03 | 2026-09-04 | 2026-08-10 | 2026-09-11 | 33 | Yes | 0 | 7 | In Progress | [27 empty] | ■ | ■ | ■ | ■ | ■ | ■
5.1 | Exterior framing and sheathing | 4.2 | 2026-08-17 | 2026-09-25 | 2026-08-24 | 2026-10-02 | 40 | Yes | 0 | 7 | In Progress | [30 empty] | ■ | ■ | ■ | ■ | ■
5.2 | Roofing system | 4.3 | 2026-08-31 | 2026-09-25 | 2026-09-03 | 2026-10-02 | 26 | Yes | 0 | 7 | In Progress | [32 empty] | ■ | ■ | ■ | ■ | ■ | ■
5.3 | Curtain wall / storefront | 5.1 | 2026-09-07 | 2026-10-16 | 2026-09-09 | 2026-10-18 | 40 | No | 7 | 2 | In Progress | [34 empty] | ■ | ■ | ■ | ■
6.1 | Underground electrical and plumbing | 2.3 | 2026-05-18 | 2026-07-17 | 2026-05-20 | 2026-07-21 | 61 | No | 7 | 4 | Complete | [35 empty] | ■ | ■ | ■ | ■ | ■
6.2 | MEP overhead rough-in - Area A | 4.3 | 2026-08-24 | 2026-10-02 | 2026-08-31 | 2026-10-09 | 40 | Yes | 0 | 7 | In Progress | [19 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
6.3 | MEP overhead rough-in - Area B | 6.2 | 2026-09-14 | 2026-10-23 | 2026-09-21 | 2026-10-30 | 40 | Yes | 0 | 7 | Not Started | [33 empty] | ■ | ■ | ■ | ■ | ■ | ■
6.4 | Main electrical gear delivery | 1.5 | 2026-05-04 | 2026-10-09 | 2026-05-04 | 2026-10-11 | 159 | Yes | 0 | 2 | In Progress | [36 empty] | ■ | ■ | ■ | ■ | ■ | ■
6.5 | AHU / RTU delivery and set | 1.5 | 2026-05-11 | 2026-09-18 | 2026-05-11 | 2026-09-20 | 131 | Yes | 0 | 2 | In Progress | [16 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
7.1 | Interior metal framing | 5.2,6.2 | 2026-09-28 | 2026-11-06 | 2026-10-05 | 2026-11-13 | 40 | Yes | 0 | 7 | Not Started | [17 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
7.2 | Drywall / tape / finish | 7.1 | 2026-10-19 | 2026-12-04 | 2026-10-26 | 2026-12-11 | 47 | Yes | 0 | 7 | Not Started | [38 empty] | ■ | ■ | ■ | ■ | ■ | ■
7.3 | Ceilings and flooring | 7.2 | 2026-11-23 | 2027-01-15 | 2026-11-23 | 2027-01-15 | 54 | No | 7 | 0 | Not Started | [41 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■
7.4 | Millwork / doors / hardware | 7.2 | 2026-11-30 | 2027-01-22 | 2026-11-30 | 2027-01-22 | 54 | No | 7 | 0 | Not Started | [45 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
7.5 | Painting and final finishes | 7.2 | 2026-12-07 | 2027-01-29 | 2026-12-07 | 2027-01-29 | 54 | No | 7 | 0 | Not Started | [46 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
8.1 | Paving, curb, sidewalks | 5.1 | 2026-10-05 | 2026-11-13 | 2026-10-05 | 2026-11-13 | 40 | No | 7 | 0 | Not Started | [47 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
8.2 | Landscaping and site furnishings | 8.1 | 2027-01-04 | 2027-02-05 | 2027-01-04 | 2027-02-05 | 33 | No | 7 | 0 | Not Started | [38 empty] | ■ | ■ | ■ | ■ | ■ | ■
9.1 | MEP startup and controls checkout | 6.4,6.5,7.3 | 2027-01-11 | 2027-02-12 | 2027-01-18 | 2027-02-19 | 33 | Yes | 0 | 7 | Not Started | [51 empty] | ■ | ■ | ■ | ■ | ■
9.2 | TAB / functional performance testing | 9.1 | 2027-02-01 | 2027-02-26 | 2027-02-08 | 2027-03-05 | 26 | Yes | 0 | 7 | Not Started | [53 empty] | ■ | ■ | ■ | ■ | ■
9.3 | Punch list and deficiency correction | 7.5,9.2 | 2027-02-15 | 2027-03-05 | 2027-02-22 | 2027-03-12 | 19 | Yes | 0 | 7 | Not Started | [56 empty] | ■ | ■ | ■ | ■
9.4 | Owner training / O&M turnover | 9.1 | 2027-02-22 | 2027-03-12 | 2027-02-22 | 2027-03-12 | 19 | No | 7 | 0 | Not Started | [58 empty] | ■ | ■ | ■
9.5 | Certificate of Occupancy | 9.3 | 2027-03-08 | 2027-03-12 | 2027-03-15 | 2027-03-19 | 5 | Yes | 0 | 7 | Not Started | [58 empty] | ■ | ■ | ■
9.6 | Final completion / handover | 9.4,9.5 | 2027-03-15 | 2027-03-19 | 2027-03-22 | 2027-03-26 | 5 | Yes | 0 | 7 | Not Started | [61 empty] | ■
■

## Earned_Value
Month | PV | EV | AC | SPI | CPI | SV | CV | EARNED VALUE PERFORMANCE ¦ STATUS DATE 09/15/2026
2026-01-01 | 450000 | 430000 | 470000 | 0.95556 | 0.91489 | -20000 | -40000
2026-02-01 | 1200000 | 1150000 | 1240000 | 0.95833 | 0.92742 | -50000 | -90000 | Metric | Value | Metric | Value
2026-03-01 | 2350000 | 2250000 | 2380000 | 0.95745 | 0.94538 | -100000 | -130000 | BAC | 20600000 | CPI | 1.2325
2026-04-01 | 4100000 | 3920000 | 4080000 | 0.9561 | 0.96078 | -180000 | -160000 | PV | 13050000 | EAC (CPI) | 16713979.3487
2026-05-01 | 6250000 | 5980000 | 6100000 | 0.9568 | 0.98033 | -270000 | -120000 | EV | 12590000 | VAC | 3886020.6513
2026-06-01 | 8350000 | 7960000 | 8050000 | 0.95329 | 0.98882 | -390000 | -90000 | AC | 10215000 | TCPI (BAC) | 0.7713
2026-07-01 | 10100000 | 9720000 | 9550000 | 0.96238 | 1.0178 | -380000 | 170000 | SPI | 0.96475 | Schedule Var. | -460000
2026-08-01 | 11850000 | 11380000 | 10050000 | 0.96034 | 1.1323 | -470000 | 1330000
2026-09-01 | 13050000 | 12590000 | 10215000 | 0.96475 | 1.2325 | -460000 | 2375000

## Completed_Forms
COMPLETED CONSTRUCTION CONTROL FORMS ¦ PORTFOLIO SAMPLES
Form ID | Type | Subject | Responsible | Status | Disposition / Key Record | Cycle Time | Cost Impact
RFI-006 | RFI | Underground utility conflict at east service yard | Civil/MEP | Closed | Relocate storm line 4'-0" south; no structural impact | 4 days | $18,500
SUB-042 | Submittal | Main switchgear product data and shop drawings | Electrical | Approved as Noted | Release fabrication with revised breaker labeling | 6 days | $0
PCO-011 | Potential Change | Owner-requested storefront finish upgrade | Owner/Glazing | Approved | Incorporated into CO-004 after pricing validation | 9 days | $95,000
DR-0915 | Daily Report | Steel/deck/envelope/MEP field operations | Superintendent | Complete | 84 workers; 0 incidents; rain 0.2 in.; south elevation recovery crew added | 1 day | N/A
MTG-028 | OAC Minutes | Weekly owner-architect-contractor meeting | PM | Complete | Decisions: protect 9/29 dry-in; maintain gear expedite gate; reject noncritical owner add | 60 min | N/A
SAMPLE OAC MEETING MINUTES ¦ 09/15/2026
Item | Topic | Discussion / Decision | Owner | Due | Status | Impact | Reference
1 | Weather-tight milestone | South elevation recovery crew approved; resequence north glazing prep in parallel. | Superintendent | 09/18/26 | Open | Protects critical path | SCH-5.1/5.2
2 | Electrical gear | Factory ship date 9/28 confirmed. Expedite only if ship date slips >3 days. | PM/Electrical | 09/22/26 | Open | Avoid unnecessary premium | PROC-004
3 | MEP clash Grid C7 | RFI response accepted; reroute duct branch before ceiling close-in. | MEP Lead | 09/17/26 | Open | 2-day local recovery | RFI-014
4 | Owner changes | Defer elective conference-room AV upgrade until contingency review. | Owner/PM | 09/21/26 | Open | Protect contingency | PCO-013
5 | Safety | Close scaffold access observation before next shift. | Superintendent | 09/16/26 | Closed | Zero recordables maintained | SAFE-008

## Portfolio_Case_Study
CORPORATE OPERATIONS CENTER ¦ CONSTRUCTION PM CASE STUDY
Project | 75,000 SF Ground-Up Corporate Operations Center
Delivery | Corporate commercial construction simulation
Baseline Budget | $20.6M
Status Date | 09/15/2026
Baseline Finish | 03/19/2027
Current Health | AMBER - schedule recovery / contingency watch
Safety | 0 recordable incidents
Role | Construction Project Manager - Portfolio Simulation
BUSINESS / DELIVERY CHALLENGE
Deliver a new corporate operations center while controlling a weather-sensitive envelope sequence, long-lead electrical equipment, active design coordination, owner changes, safety, quality, and commissioning requirements. By September, critical envelope and Area A MEP work had slipped, creating pressure on the weather-tight milestone and downstream interiors.
PM ACTIONS & CONTROLS
Built and maintained an integrated control system covering schedule, budget/forecast, procurement, RFIs, submittals, changes, risks, issues, safety, quality, meetings, stakeholders, and closeout. Used critical-path review and a recovery crew to protect dry-in; established weekly factory calls for electrical gear; enforced formal RFI/submittal and change-control gates; tracked contingency consumption and forecast-at-completion; and escalated executive decisions through a concise monthly status report.
MEASURABLE PROJECT OUTCOMES AT STATUS DATE
Metric | Result | Why it matters | PM evidence
Forecast | $20.55M FAC vs $21.057M revised budget | Forecast remains within authorized funding | Budget_Cost / Dashboard
Schedule | 49.9% actual vs 51.7% planned | 1.8 pp behind; recovery actions active | CPM_Gantt / Master_Schedule
Safety | 0 recordables | Maintains workforce and delivery continuity | Safety_Log
Controls | 3 open RFIs; long-leads released | Decision cycle and procurement exposure actively managed | RFI_Log / Procurement